## Read Me
Healthcare Application Rationalization — Sample Dataset
20 real healthcare and enterprise technology products with synthetic organization data
Prepared for: | AppRat AI Hackathon
As of: | 2026-08-14
This workbook is an analysis-ready test portfolio for a fictional global health system. Product names, vendors, and public capability descriptions are real; every organization-specific value is synthetic. No stakeholder interviews or patient-level data were used.
Sheet | Purpose | Use in prototype
App Inventory | One row per application; primary upload table | Model input
User Profiles | Access-level entitlement and 90-day usage counts | Model input
Capability Map | Many-to-many capabilities, tasks, roles, and criticality | Model input
Risks | Detailed risks, scores, mitigations, owners, and status | Model input
TCO | Cost components, annual TCO, avoidable cost, and transition cost | Model input
Dependencies | Application, data, authentication, workflow, and infrastructure dependencies | Model input
Performance & Roadmap | KPIs, lifecycle, releases, support, and contract timing | Model input
Assumptions | Definitions, thresholds, and synthetic-data controls | Reference
Data Dictionary | Mapping to every required data area | Reference
Sources | Official product pages used for public facts | Reference

## App Inventory
App ID | Application Name | Short Name | Description | Vendor | Category | Tool Type | Commercial Model | Hosting Model | Platform | Development / Configuration Language | Primary Business Unit | Application Owner | Owner Role | Owner Email | Technical SME | SME Role | SME Email | Vendor Product URL | Vendor Support URL | Primary Capability | Critical Operation Flag | Business Criticality | Business Value Score (1-5) | Business Value Rationale | Data Classification | Entitled Users | Active Users (90d) | Utilization Rate | Annual TCO | Avoidable Annual Cost | Highest Risk | Dependency Count | Availability (12mo) | SLA Target | Performance Status | Lifecycle Stage | Next Major Update | Contract Renewal Date | Evidence Confidence | Evidence Sources | Data Status
APP-001 | Epic | Epic EHR | Enterprise electronic health record supporting clinical documentation, computerized provider order entry, patient records, revenue cycle workflows, and patient engagement. | Epic Systems Corporation | Electronic Health Record | Application Platform | Commercial off-the-shelf | Private cloud / vendor-managed hosting (synthetic deployment) | Web, Windows, and mobile clinical clients; proprietary EHR platform | Vendor proprietary; customer integrations use HL7, FHIR, and APIs | Clinical Operations | Maya Chen (synthetic) | Chief Medical Information Officer | maya.chen@northstarhealth.example | Alex Romero (synthetic) | EHR Platform Architect | alex.romero@northstarhealth.example | https://www.epic.com/about/ | https://userweb.epic.com/ | Patient record management | Yes | Critical | 5 | System of record for inpatient and emergency care; direct impact to clinical operations and patient safety. | PHI / PII | 32500 | 29400 | 90.46% | 8750000 | 0 | High | 3 | 99.98% | 99.9% | Meets | Strategic Invest | 2027-03-15 | 2027-06-30 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-002 | Oracle Health EHR | Oracle EHR | Enterprise EHR supporting clinical documentation, orders, patient timelines, care coordination, and clinical decision support for acquired hospitals. | Oracle Corporation | Electronic Health Record | Application Platform | Commercial off-the-shelf | Vendor cloud / hosted (synthetic deployment) | Browser and mobile clients; proprietary Oracle Health platform | Vendor proprietary; integrations use HL7, FHIR, and APIs | Clinical Operations | Aaron Patel (synthetic) | VP, Clinical Informatics | aaron.patel@northstarhealth.example | Samira Malik (synthetic) | Oracle Health Technical Lead | samira.malik@northstarhealth.example | https://www.oracle.com/health/clinical-suite/electronic-health-record/ | https://support.oracle.com/ | Patient record management | Yes | Critical | 4 | Supports three acquired hospitals but duplicates core EHR capabilities and has below-target adoption and performance. | PHI / PII | 10200 | 7200 | 70.59% | 6500000 | 4400000 | High | 2 | 99.85% | 99.9% | Below | Consolidation Candidate | 2027-02-01 | 2027-01-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-003 | athenaOne | athenaOne | Cloud-based ambulatory suite combining EHR, practice management, revenue cycle, and patient engagement capabilities. | athenahealth, Inc. | Electronic Health Record | SaaS | Commercial SaaS | Vendor-managed SaaS | Web and mobile | Vendor proprietary; APIs, HL7, and FHIR integrations | Ambulatory Operations | Priya Shah (synthetic) | VP, Ambulatory Operations | priya.shah@northstarhealth.example | Cameron Wells (synthetic) | Ambulatory Applications Architect | cameron.wells@northstarhealth.example | https://www.athenahealth.com/solutions/athenaone | https://www.athenahealth.com/about/contact-us | Ambulatory care delivery | Yes | High | 4 | Purpose-fit for independent ambulatory affiliates with high adoption and a distinct collections-based operating model. | PHI / PII | 3000 | 2560 | 85.33% | 1500000 | 0 | Medium | 1 | 99.95% | 99.9% | Meets | Active | 2026-11-15 | 2027-03-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-004 | Microsoft Teams Enterprise | Teams | Enterprise collaboration platform for chat, channels, meetings, calling, files, and workflow integrations. | Microsoft Corporation | Collaboration | SaaS | Commercial SaaS | Vendor-managed SaaS | Web, Windows, macOS, iOS, and Android | Vendor proprietary; Power Platform, Graph API, and webhooks for extensions | Digital Workplace | Lena Ortiz (synthetic) | VP, Digital Workplace | lena.ortiz@northstarhealth.example | Noah Bennett (synthetic) | Collaboration Platform Lead | noah.bennett@northstarhealth.example | https://www.microsoft.com/en-us/microsoft-teams/enterprise | https://support.microsoft.com/teams | Enterprise collaboration | No | High | 4 | Strategic enterprise standard integrated with identity, productivity, meetings, and security controls. | Internal / possible PHI | 41500 | 34400 | 82.89% | 3830000 | 0 | Medium | 1 | 99.97% | 99.9% | Meets | Strategic Invest | 2026-10-10 | 2027-06-30 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-005 | Slack Enterprise Grid | Slack | Enterprise messaging and collaboration platform using workspaces, channels, search, file sharing, and application integrations. | Salesforce, Inc. | Collaboration | SaaS | Commercial SaaS | Vendor-managed SaaS | Web, desktop, iOS, and Android | Vendor proprietary; APIs, webhooks, and app framework | Digital Workplace | Lena Ortiz (synthetic) | VP, Digital Workplace | lena.ortiz@northstarhealth.example | Isabella Ross (synthetic) | Messaging Platform Lead | isabella.ross@northstarhealth.example | https://slack.com/enterprise | https://slack.com/help | Enterprise collaboration | No | Medium | 3 | Useful for technology teams but duplicates enterprise messaging and collaboration capabilities already available in Teams. | Internal / possible PHI | 10800 | 5320 | 49.26% | 1260000 | 820000 | High | 2 | 99.93% | 99.9% | Below | Consolidation Candidate | 2026-10-20 | 2026-12-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-006 | Zoom Workplace | Zoom | AI-enabled collaboration suite for meetings, chat, phone, whiteboards, documents, and hybrid work experiences. | Zoom Communications, Inc. | Collaboration | SaaS | Commercial SaaS | Vendor-managed SaaS | Web, desktop, mobile, and room systems | Vendor proprietary; SDKs, APIs, and webhooks | Virtual Care and Digital Workplace | Monica Reed (synthetic) | VP, Virtual Care | monica.reed@northstarhealth.example | Liam Cooper (synthetic) | Unified Communications Architect | liam.cooper@northstarhealth.example | https://www.zoom.com/en/products/collaboration-tools/ | https://support.zoom.com/ | Virtual meetings and telehealth | No | High | 3 | Overlaps with Teams, but possible telehealth and room-system dependencies require validation before a decision. | Internal / possible PHI | 25500 | 6620 | 25.96% | 1130000 | 550000 | High | 2 | 99.94% | 99.9% | Below | Review | 2026-09-25 | 2026-11-30 | Low | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-007 | Microsoft Dragon Copilot | Dragon Copilot | Clinical AI assistant combining ambient conversation capture, clinical note generation, dictation, and workflow assistance. | Microsoft Corporation | Clinical AI | AI Tool / Agent | Commercial SaaS | Vendor-managed SaaS | Web, desktop, and mobile with EHR integration | Vendor proprietary AI; EHR connectors and APIs | Clinical Transformation | Daniel Kim (synthetic) | Chief Clinical Transformation Officer | daniel.kim@northstarhealth.example | Aisha Grant (synthetic) | Clinical AI Architect | aisha.grant@northstarhealth.example | https://www.microsoft.com/en-us/health-solutions/clinical-workflow/dragon-copilot | https://support.microsoft.com/en-US/dragon-copilot/physicians/welcome-to-microsoft-dragon-copilot | Ambient clinical documentation | No | High | 5 | Strategic clinical AI standard with broad specialty coverage, strong adoption, and integration across core EHR workflows. | PHI | 3700 | 3180 | 85.95% | 1670000 | 0 | High | 2 | 99.91% | 99.5% | Meets | Strategic Invest | 2027-01-15 | 2027-02-28 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-008 | Abridge | Abridge | Generative AI platform that captures clinical conversations and drafts clinically useful notes inside EHR workflows. | Abridge AI, Inc. | Clinical AI | AI Tool / Agent | Commercial SaaS | Vendor-managed SaaS | Mobile and web with EHR integration | Vendor proprietary AI; EHR connectors and APIs | Clinical Transformation | Daniel Kim (synthetic) | Chief Clinical Transformation Officer | daniel.kim@northstarhealth.example | Aisha Grant (synthetic) | Clinical AI Architect | aisha.grant@northstarhealth.example | https://www.abridge.com/product | https://www.abridge.com/contact | Ambient clinical documentation | No | High | 4 | Provides valuable ambient documentation but overlaps the selected strategic clinical AI platform for most enrolled specialties. | PHI | 2300 | 975 | 42.39% | 740000 | 380000 | High | 1 | 99.78% | 99.5% | Below | Consolidation Candidate | 2026-11-10 | 2026-12-15 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-009 | Nabla Copilot | Nabla | Ambient clinical AI assistant that generates clinical documentation from patient-clinician conversations. | Nabla | Clinical AI | AI Tool / Agent | Commercial SaaS | Vendor-managed SaaS | Web and mobile with EHR integration | Vendor proprietary AI; EHR connectors and APIs | Clinical Transformation | Daniel Kim (synthetic) | Chief Clinical Transformation Officer | daniel.kim@northstarhealth.example | Aisha Grant (synthetic) | Clinical AI Architect | aisha.grant@northstarhealth.example | https://www.nabla.com/ | https://www.nabla.com/contact | Ambient clinical documentation | No | Low | 2 | Small pilot with low utilization and no validated unique capability beyond the enterprise clinical AI standard. | PHI | 1250 | 170 | 13.6% | 400000 | 240000 | High | 1 | 99.6% | 99.5% | Below | Pilot / Exit Candidate | 2026-12-01 | 2026-10-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-010 | Suki Assistant | Suki | Healthcare AI assistant for ambient clinical notes, dictation, coding support, and other clinician administrative tasks. | Suki AI, Inc. | Clinical AI | AI Tool / Agent | Commercial SaaS | Vendor-managed SaaS | Web and mobile with EHR integration | Vendor proprietary AI; EHR connectors and APIs | Clinical Transformation | Daniel Kim (synthetic) | Chief Clinical Transformation Officer | daniel.kim@northstarhealth.example | Aisha Grant (synthetic) | Clinical AI Architect | aisha.grant@northstarhealth.example | https://www.suki.ai/ | https://www.suki.ai/contact | Ambient clinical documentation | No | High | 3 | Useful in selected specialties but materially overlaps Dragon Copilot; migration feasibility is considered acceptable in this test scenario. | PHI | 1860 | 645 | 34.68% | 620000 | 300000 | High | 2 | 99.8% | 99.5% | Below | Consolidation Candidate | 2026-11-20 | 2027-01-15 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-011 | QGenda ProviderCloud | QGenda | Healthcare provider operations platform supporting provider scheduling, credentialing, time tracking, compensation, capacity, and workforce analytics. | QGenda, LLC | Workforce Management | SaaS | Commercial SaaS | Vendor-managed SaaS | Web and mobile | Vendor proprietary; APIs and file-based integrations | Provider Operations | Jordan Brooks (synthetic) | VP, Provider Operations | jordan.brooks@northstarhealth.example | Olivia Price (synthetic) | Provider Scheduling Lead | olivia.price@northstarhealth.example | https://www.qgenda.com/ | https://www.qgenda.com/contact-us/ | Provider scheduling | Yes | Critical | 5 | Primary provider scheduling and on-call platform with high adoption and direct linkage to staffing and patient access. | PII / Workforce | 12500 | 11480 | 91.84% | 1190000 | 0 | Medium | 2 | 99.92% | 99.9% | Meets | Active | 2027-02-20 | 2027-04-30 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-012 | UKG Pro Workforce Management | UKG WFM | Workforce management suite for time and attendance, scheduling, labor analytics, compliance, and frontline workforce operations. | UKG, Inc. | Workforce Management | SaaS | Commercial SaaS | Vendor-managed SaaS | Web, mobile, and time-clock endpoints | Vendor proprietary; APIs and integration tooling | Workforce Operations | Carla Nguyen (synthetic) | VP, Workforce Operations | carla.nguyen@northstarhealth.example | Henry Adams (synthetic) | Workforce Management Solution Architect | henry.adams@northstarhealth.example | https://www.ukg.com/products/ukg-pro-workforce-management | https://www.ukg.com/support | Time and attendance | Yes | High | 4 | Enterprise standard for timekeeping and frontline scheduling; complements rather than duplicates provider-specific QGenda workflows. | PII / Workforce | 39000 | 32950 | 84.49% | 1460000 | 0 | Medium | 1 | 99.9% | 99.9% | Below | Active | 2026-11-12 | 2027-05-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-013 | ServiceNow IT Service Management | ServiceNow ITSM | Enterprise ITSM platform for incidents, problems, changes, service requests, knowledge, assets, and configuration data. | ServiceNow, Inc. | IT Service Management | SaaS Platform | Commercial SaaS | Vendor-managed SaaS | Web and mobile on the ServiceNow AI Platform | JavaScript, configuration, Flow Designer, and REST APIs | Enterprise Technology | Ethan Cole (synthetic) | VP, IT Service Management | ethan.cole@northstarhealth.example | Sophia Turner (synthetic) | ServiceNow Platform Owner | sophia.turner@northstarhealth.example | https://www.servicenow.com/products/itsm.html | https://www.servicenow.com/support.html | IT service management | Yes | Critical | 5 | Enterprise system of action for IT support and service continuity with mature CMDB and workflow adoption. | Internal / Infrastructure | 40700 | 24650 | 60.57% | 2530000 | 0 | High | 2 | 99.96% | 99.9% | Meets | Strategic Invest | 2027-03-01 | 2027-07-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-014 | Jira Service Management | Jira SM | Service management platform for service requests, incidents, problems, changes, assets, and engineering support workflows. | Atlassian | IT Service Management | SaaS | Commercial SaaS | Vendor-managed SaaS | Web and mobile | Configuration and automation rules; REST APIs | Enterprise Technology | Ethan Cole (synthetic) | VP, IT Service Management | ethan.cole@northstarhealth.example | Lucas Perry (synthetic) | Atlassian Platform Lead | lucas.perry@northstarhealth.example | https://www.atlassian.com/software/jira/service-management | https://support.atlassian.com/jira-service-management-cloud/ | IT service management | No | Medium | 3 | Supports engineering teams but duplicates incident, request, asset, and change workflows standardized in ServiceNow. | Internal / Infrastructure | 8000 | 3330 | 41.62% | 720000 | 550000 | Medium | 2 | 99.82% | 99.9% | Below | Consolidation Candidate | 2026-10-25 | 2026-12-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-015 | Microsoft Power BI | Power BI | Enterprise business intelligence platform for governed semantic models, self-service analytics, reports, dashboards, and embedded insights. | Microsoft Corporation | Analytics | SaaS / Desktop | Commercial SaaS | Vendor-managed SaaS with desktop authoring | Power BI Service, Desktop, mobile, and embedded | DAX, Power Query M, SQL, and APIs | Enterprise Analytics | Nina Alvarez (synthetic) | VP, Enterprise Analytics | nina.alvarez@northstarhealth.example | Emma Flores (synthetic) | BI Platform Architect | emma.flores@northstarhealth.example | https://www.microsoft.com/en-us/power-platform/products/power-bi | https://learn.microsoft.com/power-bi/ | Enterprise analytics | No | High | 4 | Strategic analytics standard integrated with Microsoft identity and productivity services and broadly adopted by business users. | PHI / PII / Internal | 24000 | 16200 | 67.5% | 820000 | 0 | High | 1 | 99.95% | 99.9% | Meets | Strategic Invest | 2026-09-30 | 2027-06-30 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-016 | Tableau Cloud | Tableau | Hosted visual analytics platform for data exploration, dashboards, metrics, and governed sharing of insights. | Salesforce, Inc. | Analytics | SaaS / Desktop | Commercial SaaS | Vendor-managed SaaS with desktop authoring | Tableau Cloud, Desktop, and mobile | Tableau calculations, SQL, and APIs | Enterprise Analytics | Nina Alvarez (synthetic) | VP, Enterprise Analytics | nina.alvarez@northstarhealth.example | Mateo Rivera (synthetic) | Tableau Platform Lead | mateo.rivera@northstarhealth.example | https://www.tableau.com/products/tableau | https://www.tableau.com/support | Enterprise analytics | No | Medium | 3 | Rich visual analytics capability, but low adoption and material overlap with the selected Power BI enterprise standard. | PHI / PII / Internal | 9800 | 2800 | 28.57% | 1040000 | 750000 | High | 1 | 99.88% | 99.9% | Below | Consolidation Candidate | 2027-01-20 | 2027-02-28 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-017 | Workday Human Capital Management | Workday HCM | Cloud HCM suite for core HR, talent, benefits, workforce data, reporting, and employee lifecycle processes. | Workday, Inc. | Human Capital Management | SaaS Platform | Commercial SaaS | Vendor-managed SaaS | Web and mobile | Configuration, reports, Workday integration tooling, and APIs | Human Resources | Renee Morgan (synthetic) | Chief Human Resources Officer | renee.morgan@northstarhealth.example | Grace Howard (synthetic) | Workday Solution Architect | grace.howard@northstarhealth.example | https://www.workday.com/en-us/products/human-capital-management/overview.html | https://www.workday.com/en-us/customer-experience/support.html | Human capital management | Yes | Critical | 5 | Strategic enterprise HCM platform and target state for global worker data, talent, and employee lifecycle processes. | PII / Workforce | 40200 | 36150 | 89.93% | 2700000 | 0 | High | 1 | 99.97% | 99.9% | Meets | Strategic Invest | 2027-03-15 | 2027-08-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-018 | Oracle PeopleSoft HCM | PeopleSoft HCM | Legacy HCM platform supporting core HR, payroll, benefits, and workforce administration for selected business units. | Oracle Corporation | Human Capital Management | Application Platform | Commercial off-the-shelf | Customer-hosted private cloud (synthetic deployment) | PeopleSoft HCM on PeopleTools with web access | PeopleCode, PeopleTools configuration, SQL, and integrations | Human Resources | Renee Morgan (synthetic) | Chief Human Resources Officer | renee.morgan@northstarhealth.example | Victor James (synthetic) | PeopleSoft Technical Lead | victor.james@northstarhealth.example | https://www.oracle.com/applications/peoplesoft/ | https://support.oracle.com/ | Human capital management | Yes | High | 3 | Still supports payroll for two regions but duplicates Workday target-state capabilities and carries significant technical debt. | PII / Workforce | 8700 | 4620 | 53.1% | 2780000 | 1400000 | Critical | 1 | 99.7% | 99.9% | Below | Replace / Sunset | 2027-09-01 | 2027-12-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-019 | Salesforce Health Cloud | Health Cloud | Healthcare CRM and engagement platform with healthcare data models, care coordination, referral workflows, patient engagement, and AI-enabled automation. | Salesforce, Inc. | Healthcare CRM | SaaS Platform | Commercial SaaS | Vendor-managed SaaS | Salesforce cloud, web, and mobile | Flow, Apex, Lightning Web Components, configuration, and APIs | Patient Access and Engagement | Alicia Grant (synthetic) | VP, Patient Access and Engagement | alicia.grant@northstarhealth.example | Chloe Martin (synthetic) | Salesforce Health Cloud Architect | chloe.martin@northstarhealth.example | https://www.salesforce.com/healthcare/cloud/ | https://help.salesforce.com/ | Patient engagement and care coordination | No | High | 4 | Distinct engagement and care-coordination layer that extends rather than replaces the EHR system of record. | PHI / PII | 5100 | 4050 | 79.41% | 2050000 | 0 | High | 2 | 99.92% | 99.9% | Meets | Active | 2026-10-15 | 2027-03-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data
APP-020 | Imprivata Enterprise Access Management | Imprivata EAM | Healthcare access management platform providing single sign-on, multifactor and passwordless authentication, badge access, and shared-workstation workflows. | Imprivata, Inc. | Access Management | Application Platform | Commercial off-the-shelf | Hybrid: on-premises connectors with vendor cloud services (synthetic deployment) | Windows endpoints, virtual desktops, web applications, and identity integrations | Vendor proprietary; connectors, policies, and APIs | Cybersecurity and Clinical Technology | Marcus Lee (synthetic) | Chief Information Security Officer | marcus.lee@northstarhealth.example | Owen Scott (synthetic) | Clinical Access Management Architect | owen.scott@northstarhealth.example | https://www.imprivata.com/products/access-management/enterprise-access-management | https://www.imprivata.com/support | Clinical identity and access management | Yes | Critical | 5 | Enables rapid secure access to critical clinical systems and shared workstations; high downstream dependency count. | Security / Identity | 32300 | 30290 | 93.78% | 1560000 | 0 | High | 2 | 99.99% | 99.9% | Meets | Strategic Invest | 2027-02-10 | 2027-05-31 | High | CMDB; IAM/SSO; contracts; service desk; scans; integration catalog — all synthetic | Real product; synthetic organization data

## User Profiles
App ID | Application Name | User Population | Access Level | Entitled Users | Active Users (90d) | Inactive Users (90d) | Avg Weekly Sessions / Active User | Avg Monthly Transactions | Region | Evidence Source | Evidence Confidence
APP-001 | Epic | Platform administrators and super users | Power user | 4500 | 4200 | 300 | 18 | 672000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-001 | Epic | Business and clinical end users | Regular user | 28000 | 25200 | 2800 | 10 | 2620800 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-002 | Oracle Health EHR | Platform administrators and super users | Power user | 1200 | 900 | 300 | 14 | 108000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-002 | Oracle Health EHR | Business and clinical end users | Regular user | 9000 | 6300 | 2700 | 8 | 491400 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-003 | athenaOne | Platform administrators and super users | Power user | 300 | 260 | 40 | 12 | 24700 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-003 | athenaOne | Business and clinical end users | Regular user | 2700 | 2300 | 400 | 7 | 142025 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-004 | Microsoft Teams Enterprise | Platform administrators and super users | Power user | 1500 | 1400 | 100 | 20 | 182000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-004 | Microsoft Teams Enterprise | Business and clinical end users | Regular user | 40000 | 33000 | 7000 | 11 | 2788500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-005 | Slack Enterprise Grid | Platform administrators and super users | Power user | 800 | 620 | 180 | 17 | 55800 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-005 | Slack Enterprise Grid | Business and clinical end users | Regular user | 10000 | 4700 | 5300 | 9 | 274950 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-006 | Zoom Workplace | Platform administrators and super users | Power user | 500 | 420 | 80 | 10 | 23100 | Global | IAM / SSO telemetry; license export; synthetic values | Low
APP-006 | Zoom Workplace | Business and clinical end users | Regular user | 25000 | 6200 | 18800 | 6 | 221650 | Global | IAM / SSO telemetry; license export; synthetic values | Low
APP-007 | Microsoft Dragon Copilot | Platform administrators and super users | Power user | 200 | 180 | 20 | 22 | 22500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-007 | Microsoft Dragon Copilot | Business and clinical end users | Regular user | 3500 | 3000 | 500 | 12 | 243750 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-008 | Abridge | Platform administrators and super users | Power user | 100 | 75 | 25 | 15 | 5850 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-008 | Abridge | Business and clinical end users | Regular user | 2200 | 900 | 1300 | 8 | 45630 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-009 | Nabla Copilot | Platform administrators and super users | Power user | 50 | 20 | 30 | 7 | 640 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-009 | Nabla Copilot | Business and clinical end users | Regular user | 1200 | 150 | 1050 | 4 | 3120 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-010 | Suki Assistant | Platform administrators and super users | Power user | 60 | 45 | 15 | 11 | 2700 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-010 | Suki Assistant | Business and clinical end users | Regular user | 1800 | 600 | 1200 | 6 | 23400 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-011 | QGenda ProviderCloud | Platform administrators and super users | Power user | 500 | 480 | 20 | 19 | 69600 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-011 | QGenda ProviderCloud | Business and clinical end users | Regular user | 12000 | 11000 | 1000 | 10 | 1036750 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-012 | UKG Pro Workforce Management | Platform administrators and super users | Power user | 1000 | 950 | 50 | 16 | 104500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-012 | UKG Pro Workforce Management | Business and clinical end users | Regular user | 38000 | 32000 | 6000 | 9 | 2288000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-013 | ServiceNow IT Service Management | Platform administrators and super users | Power user | 700 | 650 | 50 | 24 | 97500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-013 | ServiceNow IT Service Management | Business and clinical end users | Regular user | 40000 | 24000 | 16000 | 13 | 2340000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-014 | Jira Service Management | Platform administrators and super users | Power user | 500 | 430 | 70 | 18 | 43000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-014 | Jira Service Management | Business and clinical end users | Regular user | 7500 | 2900 | 4600 | 10 | 188500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-015 | Microsoft Power BI | Platform administrators and super users | Power user | 2000 | 1700 | 300 | 14 | 144500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-015 | Microsoft Power BI | Business and clinical end users | Regular user | 22000 | 14500 | 7500 | 8 | 801125 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-016 | Tableau Cloud | Platform administrators and super users | Power user | 800 | 500 | 300 | 11 | 35000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-016 | Tableau Cloud | Business and clinical end users | Regular user | 9000 | 2300 | 6700 | 6 | 104650 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-017 | Workday Human Capital Management | Platform administrators and super users | Power user | 1200 | 1150 | 50 | 13 | 103500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-017 | Workday Human Capital Management | Business and clinical end users | Regular user | 39000 | 35000 | 4000 | 7 | 2047500 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-018 | Oracle PeopleSoft HCM | Platform administrators and super users | Power user | 700 | 520 | 180 | 12 | 39000 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-018 | Oracle PeopleSoft HCM | Business and clinical end users | Regular user | 8000 | 4100 | 3900 | 7 | 199875 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-019 | Salesforce Health Cloud | Platform administrators and super users | Power user | 600 | 550 | 50 | 16 | 57750 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-019 | Salesforce Health Cloud | Business and clinical end users | Regular user | 4500 | 3500 | 1000 | 9 | 238875 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-020 | Imprivata Enterprise Access Management | Platform administrators and super users | Power user | 300 | 290 | 10 | 30 | 52200 | Global | IAM / SSO telemetry; license export; synthetic values | High
APP-020 | Imprivata Enterprise Access Management | Business and clinical end users | Regular user | 32000 | 30000 | 2000 | 17 | 3510000 | Global | IAM / SSO telemetry; license export; synthetic values | High

## Capability Map
App ID | Application Name | Capability ID | Capability | Process / Tasks Enabled | Support Role | Coverage Level | Capability Criticality | Critical Operation Flag | Evidence Source | Evidence Confidence | Data Status
APP-001 | Epic | CAP-001 | Patient record management | Maintain longitudinal patient chart, results, medications, and encounter history | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-001 | Epic | CAP-002 | Clinical documentation | Create, review, sign, and retrieve clinical notes | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-001 | Epic | CAP-003 | Clinical order management | Enter, route, verify, and track orders | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-001 | Epic | CAP-004 | Revenue cycle operations | Capture charges, code encounters, and support billing workflows | Secondary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-002 | Oracle Health EHR | CAP-001 | Patient record management | Maintain patient chart and clinical history at acquired hospitals | Duplicative | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-002 | Oracle Health EHR | CAP-002 | Clinical documentation | Create and sign clinical notes | Duplicative | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-002 | Oracle Health EHR | CAP-003 | Clinical order management | Enter and manage orders | Duplicative | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-002 | Oracle Health EHR | CAP-005 | Care coordination | Share clinical context and coordinate care teams | Secondary | Partial | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-003 | athenaOne | CAP-006 | Ambulatory care delivery | Support outpatient encounters, specialty workflows, and patient charts | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-003 | athenaOne | CAP-004 | Revenue cycle operations | Submit claims, manage billing, and track collections | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-003 | athenaOne | CAP-007 | Patient engagement | Provide portal, messaging, reminders, payments, and telehealth | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-004 | Microsoft Teams Enterprise | CAP-008 | Enterprise collaboration | Chat, channels, files, and team workspaces | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-004 | Microsoft Teams Enterprise | CAP-009 | Virtual meetings | Host internal and external meetings and calls | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-004 | Microsoft Teams Enterprise | CAP-010 | Workflow collaboration | Connect business workflows and notifications to collaboration spaces | Primary | Full | Medium | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-005 | Slack Enterprise Grid | CAP-008 | Enterprise collaboration | Chat, channels, search, files, and team workspaces | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-005 | Slack Enterprise Grid | CAP-010 | Workflow collaboration | Connect engineering and support workflows to channels | Duplicative | Partial | Medium | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-006 | Zoom Workplace | CAP-009 | Virtual meetings | Host meetings, webinars, and room-based collaboration | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | Low | Synthetic organization mapping
APP-006 | Zoom Workplace | CAP-011 | Virtual care communications | Support selected telehealth and patient-facing video workflows | Secondary | Partial | High | No | Product documentation; process taxonomy; synthetic mapping | Low | Synthetic organization mapping
APP-006 | Zoom Workplace | CAP-008 | Enterprise collaboration | Provide chat and asynchronous collaboration | Duplicative | Partial | High | No | Product documentation; process taxonomy; synthetic mapping | Low | Synthetic organization mapping
APP-007 | Microsoft Dragon Copilot | CAP-012 | Ambient clinical documentation | Capture clinical conversations and draft structured notes | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-007 | Microsoft Dragon Copilot | CAP-013 | Medical dictation | Convert clinician speech to text and commands | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-007 | Microsoft Dragon Copilot | CAP-014 | Clinical workflow assistance | Summarize context and assist with administrative tasks | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-008 | Abridge | CAP-012 | Ambient clinical documentation | Capture conversations and generate note drafts in the EHR | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-008 | Abridge | CAP-014 | Clinical workflow assistance | Provide encounter summaries and linked evidence | Duplicative | Partial | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-009 | Nabla Copilot | CAP-012 | Ambient clinical documentation | Capture conversations and generate note drafts | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-009 | Nabla Copilot | CAP-014 | Clinical workflow assistance | Support documentation review and coding prompts | Duplicative | Partial | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-010 | Suki Assistant | CAP-012 | Ambient clinical documentation | Generate notes from ambient conversations | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-010 | Suki Assistant | CAP-013 | Medical dictation | Support voice dictation in clinical workflows | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-010 | Suki Assistant | CAP-014 | Clinical workflow assistance | Assist with coding and clinical administrative tasks | Duplicative | Partial | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-011 | QGenda ProviderCloud | CAP-015 | Provider scheduling | Create provider schedules, manage on-call coverage, and fill gaps | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-011 | QGenda ProviderCloud | CAP-016 | Provider credentialing | Track provider credentials and readiness to practice | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-011 | QGenda ProviderCloud | CAP-017 | Provider capacity management | Match provider availability to demand and locations | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-012 | UKG Pro Workforce Management | CAP-018 | Time and attendance | Capture time, apply pay rules, and route approvals | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-012 | UKG Pro Workforce Management | CAP-019 | Frontline workforce scheduling | Schedule nursing and non-provider workforce | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-012 | UKG Pro Workforce Management | CAP-020 | Labor compliance analytics | Monitor labor rules, overtime, and staffing compliance | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-013 | ServiceNow IT Service Management | CAP-021 | IT service management | Manage requests, incidents, problems, changes, and knowledge | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-013 | ServiceNow IT Service Management | CAP-022 | Configuration management | Maintain service and dependency records in the CMDB | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-013 | ServiceNow IT Service Management | CAP-023 | IT service automation | Automate triage, approvals, routing, and remediation | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-014 | Jira Service Management | CAP-021 | IT service management | Manage engineering requests, incidents, and changes | Duplicative | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-014 | Jira Service Management | CAP-022 | Configuration management | Track engineering assets and service relationships | Duplicative | Partial | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-014 | Jira Service Management | CAP-023 | IT service automation | Automate ticket routing and DevOps workflows | Duplicative | Partial | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-015 | Microsoft Power BI | CAP-024 | Enterprise analytics | Create governed models, reports, dashboards, and self-service analysis | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-015 | Microsoft Power BI | CAP-025 | Operational performance reporting | Monitor clinical, financial, and administrative KPIs | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-016 | Tableau Cloud | CAP-024 | Enterprise analytics | Create visual analytics and dashboards | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-016 | Tableau Cloud | CAP-025 | Operational performance reporting | Monitor clinical and administrative KPIs | Duplicative | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-017 | Workday Human Capital Management | CAP-026 | Human capital management | Manage worker records, organizations, jobs, and employee lifecycle | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-017 | Workday Human Capital Management | CAP-027 | Talent management | Recruit, onboard, develop, and retain the workforce | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-017 | Workday Human Capital Management | CAP-028 | Payroll and benefits administration | Manage payroll inputs, benefits, and compensation processes | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-018 | Oracle PeopleSoft HCM | CAP-026 | Human capital management | Manage legacy worker records and HR transactions | Duplicative | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-018 | Oracle PeopleSoft HCM | CAP-028 | Payroll and benefits administration | Run payroll and benefits for two regions | Duplicative | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-018 | Oracle PeopleSoft HCM | CAP-027 | Talent management | Support selected legacy talent processes | Duplicative | Partial | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-019 | Salesforce Health Cloud | CAP-007 | Patient engagement | Manage outreach, contact-center context, and personalized communications | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-019 | Salesforce Health Cloud | CAP-005 | Care coordination | Manage care plans, referrals, tasks, and cross-team collaboration | Primary | Full | High | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-019 | Salesforce Health Cloud | CAP-029 | Healthcare relationship management | Maintain patient, provider, and community relationships | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-020 | Imprivata Enterprise Access Management | CAP-030 | Clinical identity and access management | Provide SSO, MFA, passwordless access, and rapid user switching | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-020 | Imprivata Enterprise Access Management | CAP-031 | Shared workstation access | Authenticate and switch clinical users on shared endpoints | Primary | Full | Critical | Yes | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping
APP-020 | Imprivata Enterprise Access Management | CAP-032 | Access security analytics | Monitor authentication patterns and policy compliance | Primary | Full | High | No | Product documentation; process taxonomy; synthetic mapping | High | Synthetic organization mapping

## Risks
Risk ID | App ID | Application Name | Risk Category | Risk Description | Severity Score (1-5) | Likelihood Score (1-5) | Inherent Risk Score | Risk Level | Mitigation Plan | Mitigation Owner | Status | Mitigation Due Date | Residual Risk | Evidence Source | Data Status
RISK-001 | APP-001 | Epic | Security | Concentration of PHI and privileged clinical access creates high breach impact. | 5 | 3 | 15 | High | Enforce MFA, privileged-access reviews, segmentation, and quarterly access recertification. | Cybersecurity | Mitigating | 2026-12-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-002 | APP-001 | Epic | Business Continuity | An extended EHR outage would disrupt documentation, orders, and patient flow. | 5 | 2 | 10 | Medium | Maintain tested downtime workflows, redundant hosting, and semiannual disaster recovery exercises. | Clinical Technology | Mitigating | 2026-11-30 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-003 | APP-002 | Oracle Health EHR | Technical | Extensive local customizations increase upgrade effort and migration complexity. | 4 | 4 | 16 | High | Inventory customizations, retire unused extensions, and map required workflows to the target EHR. | Clinical Informatics | Open | 2026-10-31 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-004 | APP-002 | Oracle Health EHR | Business Continuity | Interface instability can delay orders and results at acquired hospitals. | 5 | 3 | 15 | High | Prioritize interface monitoring, reconciliation, and staged migration with rollback plans. | Integration Services | Mitigating | 2026-11-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-005 | APP-003 | athenaOne | Vendor | Collections-based commercial model and vendor dependency may constrain cost predictability. | 3 | 3 | 9 | Medium | Model volume sensitivity and confirm exit/data portability terms before renewal. | Ambulatory Operations | Open | 2026-12-01 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-006 | APP-003 | athenaOne | Security | Cloud EHR stores PHI and requires strong access and third-party risk controls. | 4 | 2 | 8 | Medium | Complete annual vendor security review and enforce SSO/MFA and role-based access. | Cybersecurity | Mitigating | 2026-10-15 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-007 | APP-004 | Microsoft Teams Enterprise | Security | Broad collaboration and external sharing can expose sensitive information. | 4 | 3 | 12 | High | Apply sensitivity labels, DLP, external-sharing controls, and retention policies. | Cybersecurity | Mitigating | 2026-10-31 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-008 | APP-004 | Microsoft Teams Enterprise | Operational | Tenant-wide service disruption would affect enterprise communications. | 4 | 2 | 8 | Medium | Maintain outage communications channels and documented fallback procedures. | Digital Workplace | Accepted | 2026-12-31 | Low | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-009 | APP-005 | Slack Enterprise Grid | Regulatory | Unmanaged channels and retention settings can create PHI and eDiscovery exposure. | 4 | 4 | 16 | High | Restrict PHI use, enforce enterprise retention, archive required content, and review apps. | Legal and Cybersecurity | Open | 2026-10-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-010 | APP-005 | Slack Enterprise Grid | Technical | Fourteen workflow integrations create migration and retirement complexity. | 3 | 4 | 12 | High | Inventory integrations and migrate required workflows to Teams or ServiceNow. | Digital Workplace | Open | 2026-11-30 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-011 | APP-006 | Zoom Workplace | Regulatory | Recorded meetings or telehealth sessions may contain PHI with inconsistent retention. | 5 | 3 | 15 | High | Validate telehealth workflows, disable unnecessary recording, and enforce retention controls. | Virtual Care | Open | 2026-09-30 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-012 | APP-006 | Zoom Workplace | Dependency | Room systems and external patient workflows may not be fully replaceable by Teams. | 4 | 4 | 16 | High | Complete device, workflow, and contract dependency validation before committing savings. | Unified Communications | Open | 2026-10-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-013 | APP-007 | Microsoft Dragon Copilot | AI / Clinical Safety | Generated notes may contain omissions or incorrect clinical statements. | 5 | 3 | 15 | High | Require clinician review, monitor edit rates and safety events, and maintain approved-use policies. | Clinical AI Governance | Mitigating | 2026-09-30 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-014 | APP-007 | Microsoft Dragon Copilot | Privacy | Ambient capture processes PHI and may create consent or data-handling risk. | 5 | 2 | 10 | Medium | Validate consent, retention, model-use terms, encryption, and audit logging. | Privacy Office | Mitigating | 2026-10-31 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-015 | APP-008 | Abridge | AI / Clinical Safety | Draft notes require clinician validation and specialty-specific quality monitoring. | 5 | 3 | 15 | High | Use human review, quality sampling, specialty templates, and safety incident escalation. | Clinical AI Governance | Mitigating | 2026-10-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-016 | APP-008 | Abridge | Vendor | Overlapping clinical AI contract creates cost and data-governance fragmentation. | 4 | 3 | 12 | High | Consolidate governance and migrate validated specialties to the strategic platform. | Clinical Transformation | Open | 2026-11-15 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-017 | APP-009 | Nabla Copilot | AI / Clinical Safety | Low-volume pilot has insufficient evidence to validate note quality across specialties. | 5 | 3 | 15 | High | Stop expansion, complete pilot review, export required data, and retain clinician signoff. | Clinical AI Governance | Open | 2026-09-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-018 | APP-009 | Nabla Copilot | Vendor | Small pilot adds PHI processor and contract without a unique validated capability. | 4 | 4 | 16 | High | Terminate pilot after data export and vendor offboarding checks. | Vendor Management | Open | 2026-10-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-019 | APP-010 | Suki Assistant | AI / Clinical Safety | Note quality varies by specialty and requires ongoing human review. | 5 | 3 | 15 | High | Track acceptance rates, review high-risk specialties, and retain clinician attestation. | Clinical AI Governance | Mitigating | 2026-10-31 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-020 | APP-010 | Suki Assistant | Dependency | Specialty templates and EHR integrations must be migrated before consolidation. | 4 | 3 | 12 | High | Map specialty workflows, test target templates, and stage user migration. | Clinical Transformation | Open | 2026-12-01 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-021 | APP-011 | QGenda ProviderCloud | Business Continuity | Scheduling outage could disrupt on-call coverage and patient access. | 5 | 2 | 10 | Medium | Maintain resilient access, export contingency schedules, and test downtime procedures. | Provider Operations | Mitigating | 2026-11-30 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-022 | APP-011 | QGenda ProviderCloud | Data Quality | Incorrect provider, credential, or availability data can produce unsafe schedules. | 4 | 3 | 12 | High | Automate source reconciliation and assign daily exception ownership. | Provider Operations | Mitigating | 2026-10-31 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-023 | APP-012 | UKG Pro Workforce Management | Regulatory | Incorrect time and pay rules can create wage-and-hour compliance exposure. | 4 | 3 | 12 | High | Centralize rule governance, regression test changes, and audit exceptions. | Workforce Operations | Mitigating | 2026-12-15 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-024 | APP-012 | UKG Pro Workforce Management | Business Continuity | Timekeeping disruption can delay payroll and staffing decisions. | 4 | 2 | 8 | Medium | Maintain time-clock resilience and documented manual capture procedures. | Workforce Operations | Accepted | 2027-01-15 | Low | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-025 | APP-013 | ServiceNow IT Service Management | Security | ITSM and CMDB contain privileged infrastructure and service relationship data. | 4 | 3 | 12 | High | Restrict privileged roles, monitor exports, and review integrations and AI agent permissions. | Cybersecurity | Mitigating | 2026-10-31 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-026 | APP-013 | ServiceNow IT Service Management | Business Continuity | ITSM outage would reduce incident coordination during a technology disruption. | 5 | 2 | 10 | Medium | Maintain external incident communications and emergency runbooks. | IT Service Management | Mitigating | 2026-11-15 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-027 | APP-014 | Jira Service Management | Technical | Duplicate service catalogs and asset records create conflicting operational data. | 3 | 4 | 12 | High | Reconcile records and designate ServiceNow as the system of record. | IT Service Management | Open | 2026-11-30 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-028 | APP-014 | Jira Service Management | Security | Engineering integrations and automation tokens may remain active after consolidation. | 4 | 3 | 12 | High | Inventory tokens, rotate secrets, and decommission obsolete integrations. | Cybersecurity | Open | 2026-12-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-029 | APP-015 | Microsoft Power BI | Security | Broad self-service access can expose PHI through incorrectly governed datasets. | 5 | 3 | 15 | High | Use certified datasets, row-level security, DLP, and periodic access reviews. | Data Governance | Mitigating | 2026-10-31 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-030 | APP-015 | Microsoft Power BI | Data Quality | Uncontrolled semantic models can produce conflicting measures. | 4 | 3 | 12 | High | Certify enterprise models and retire duplicate measures and workspaces. | Enterprise Analytics | Mitigating | 2026-12-01 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-031 | APP-016 | Tableau Cloud | Security | Legacy workbooks may embed extracts containing PHI with inconsistent controls. | 5 | 3 | 15 | High | Inventory extracts, migrate governed content, and securely delete retired copies. | Data Governance | Open | 2026-11-30 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-032 | APP-016 | Tableau Cloud | Technical | Low-use dashboards rely on custom extracts and manual refreshes. | 3 | 4 | 12 | High | Prioritize dashboards, rebuild required content in Power BI, and validate refresh logic. | Enterprise Analytics | Open | 2027-01-15 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-033 | APP-017 | Workday Human Capital Management | Security | Centralized global workforce data creates high privacy and privileged-access impact. | 5 | 3 | 15 | High | Apply least privilege, segregation of duties, encryption, and quarterly access reviews. | HR Security | Mitigating | 2026-11-30 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-034 | APP-017 | Workday Human Capital Management | Dependency | Payroll, benefits, scheduling, and identity integrations create a large change blast radius. | 4 | 3 | 12 | High | Maintain integration monitoring and end-to-end release regression testing. | HR Technology | Mitigating | 2027-01-31 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-035 | APP-018 | Oracle PeopleSoft HCM | Technical | Legacy customizations, batch jobs, and scarce skills increase failure and change risk. | 5 | 4 | 20 | Critical | Freeze nonessential customization, document jobs, and execute a phased Workday migration. | HR Technology | Open | 2026-10-31 | Critical | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-036 | APP-018 | Oracle PeopleSoft HCM | Business Continuity | Payroll interfaces are critical and require parallel-run validation before replacement. | 5 | 3 | 15 | High | Complete two parallel payroll cycles and reconcile benefits and bank interfaces. | Payroll Operations | Open | 2027-06-30 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-037 | APP-019 | Salesforce Health Cloud | Security | Patient engagement workflows aggregate PHI and identity data from multiple systems. | 5 | 3 | 15 | High | Apply field-level access, encryption, consent controls, and monitoring. | Cybersecurity | Mitigating | 2026-11-15 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-038 | APP-019 | Salesforce Health Cloud | Data Quality | EHR and CRM identity matching may create duplicate or incorrect patient records. | 4 | 3 | 12 | High | Use governed matching rules, stewardship queues, and reconciliation metrics. | Patient Access | Mitigating | 2026-12-15 | Medium | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-039 | APP-020 | Imprivata Enterprise Access Management | Business Continuity | Access-management outage could prevent clinicians from reaching multiple critical systems. | 5 | 4 | 20 | Critical | Implement redundancy, break-glass access, endpoint fallback, and quarterly failover tests. | Clinical Technology | Mitigating | 2026-09-30 | Critical | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk
RISK-040 | APP-020 | Imprivata Enterprise Access Management | Security | Compromised authentication policy or badge workflow has an enterprise-wide blast radius. | 5 | 3 | 15 | High | Use change control, policy testing, privileged-access monitoring, and rapid rollback. | Cybersecurity | Mitigating | 2026-10-31 | High | Security scan / BCP record / service desk evidence; synthetic assessment | Synthetic organization risk

## TCO
App ID | Application Name | Annual License / Subscription | Annual Maintenance | Annual Infrastructure / Hosting | Annual Vendor Services | Annual Internal Labor | Annual Education / Training | Annual TCO | Avoidable Annual Cost | Avoidable % of TCO | One-Time Transition Cost | First-Year Net Savings | Cost Notes | Evidence Source | Evidence Confidence
APP-001 | Epic | 5200000 | 800000 | 900000 | 400000 | 1300000 | 150000 | 8750000 | 0 | 0% | 0 | 0 | Strategic platform; no committed savings. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-002 | Oracle Health EHR | 3600000 | 700000 | 800000 | 300000 | 1000000 | 100000 | 6500000 | 4400000 | 67.69% | 2200000 | 2200000 | Avoidable after EHR migration, interface cutover, and contract exit. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-003 | athenaOne | 1000000 | 100000 | 50000 | 120000 | 200000 | 30000 | 1500000 | 0 | 0% | 0 | 0 | Distinct ambulatory operating model. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-004 | Microsoft Teams Enterprise | 3200000 | 50000 | 50000 | 120000 | 350000 | 60000 | 3830000 | 0 | 0% | 0 | 0 | Strategic collaboration standard. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-005 | Slack Enterprise Grid | 1000000 | 20000 | 10000 | 50000 | 150000 | 30000 | 1260000 | 820000 | 65.08% | 220000 | 600000 | Savings exclude retained archive and migration support. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-006 | Zoom Workplace | 850000 | 40000 | 20000 | 80000 | 120000 | 20000 | 1130000 | 550000 | 48.67% | 180000 | 370000 | Potential only; not safe until telehealth and room dependencies are validated. | Contract ledger; AP spend; labor estimate; synthetic values | Low
APP-007 | Microsoft Dragon Copilot | 1250000 | 50000 | 20000 | 80000 | 220000 | 50000 | 1670000 | 0 | 0% | 0 | 0 | Strategic clinical AI investment. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-008 | Abridge | 550000 | 20000 | 10000 | 60000 | 80000 | 20000 | 740000 | 380000 | 51.35% | 120000 | 260000 | Avoidable after provider and template migration. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-009 | Nabla Copilot | 300000 | 10000 | 0 | 30000 | 50000 | 10000 | 400000 | 240000 | 60% | 30000 | 210000 | Pilot can be exited after data export and vendor offboarding. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-010 | Suki Assistant | 450000 | 20000 | 10000 | 50000 | 70000 | 20000 | 620000 | 300000 | 48.39% | 100000 | 200000 | Avoidable after specialty workflow migration. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-011 | QGenda ProviderCloud | 850000 | 50000 | 20000 | 90000 | 150000 | 30000 | 1190000 | 0 | 0% | 0 | 0 | Provider operations platform retained. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-012 | UKG Pro Workforce Management | 950000 | 80000 | 40000 | 100000 | 250000 | 40000 | 1460000 | 0 | 0% | 0 | 0 | Enterprise workforce-management standard. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-013 | ServiceNow IT Service Management | 1600000 | 120000 | 30000 | 200000 | 500000 | 80000 | 2530000 | 0 | 0% | 0 | 0 | Strategic ITSM platform. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-014 | Jira Service Management | 480000 | 20000 | 10000 | 50000 | 140000 | 20000 | 720000 | 550000 | 76.39% | 160000 | 390000 | Includes licenses plus avoidable support effort; migrate engineering workflows first. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-015 | Microsoft Power BI | 550000 | 10000 | 20000 | 40000 | 180000 | 20000 | 820000 | 0 | 0% | 0 | 0 | Strategic analytics standard. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-016 | Tableau Cloud | 700000 | 30000 | 20000 | 60000 | 200000 | 30000 | 1040000 | 750000 | 72.12% | 220000 | 530000 | Avoidable after dashboard migration and extract retirement. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-017 | Workday Human Capital Management | 1900000 | 140000 | 30000 | 180000 | 400000 | 50000 | 2700000 | 0 | 0% | 0 | 0 | Strategic HCM platform. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-018 | Oracle PeopleSoft HCM | 450000 | 650000 | 550000 | 200000 | 850000 | 80000 | 2780000 | 1400000 | 50.36% | 650000 | 750000 | Avoidable after payroll, benefits, and regional HR migration. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-019 | Salesforce Health Cloud | 1400000 | 80000 | 20000 | 150000 | 350000 | 50000 | 2050000 | 0 | 0% | 0 | 0 | Distinct patient-engagement and care-coordination capabilities. | Contract ledger; AP spend; labor estimate; synthetic values | High
APP-020 | Imprivata Enterprise Access Management | 900000 | 100000 | 120000 | 80000 | 320000 | 40000 | 1560000 | 0 | 0% | 0 | 0 | Critical enterprise access dependency. | Contract ledger; AP spend; labor estimate; synthetic values | High
Portfolio Annual TCO | [7 empty] | 43250000
Potential Avoidable Annual Cost | [8 empty] | 9390000
Potential First-Year Net Savings | [11 empty] | 5510000
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Avoidable annual cost is recurring run-rate spend that can actually be eliminated after the recommendation is completed. It excludes continuing costs and one-time transition costs.

## Dependencies
Dependency ID | Source App ID | Source Application | Target App / System ID | Target Application / System | Dependency Type | Direction | Criticality | Disruption Impact | Data / Service Exchanged | Migration Feasibility | Required Before Disposition | Evidence Source | Evidence Confidence | Data Status
DEP-001 | APP-001 | Epic | APP-020 | Imprivata Enterprise Access Management | Authentication | Consumes | Critical | Clinicians may be unable to access Epic on shared workstations. | Identity assertions and badge authentication | Medium | Maintain break-glass access and failover. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-002 | APP-001 | Epic | EXT-001 | Enterprise Integration Engine | Data / Interface | Consumes | Critical | Orders, results, ADT, and downstream feeds may stop. | HL7 and FHIR clinical messages | Low | Cut over and reconcile all interfaces. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-003 | APP-001 | Epic | EXT-002 | Enterprise PACS | Data / Workflow | Consumes | Critical | Diagnostic images may not be available in clinical workflows. | Imaging orders, reports, and links | Low | Validate image and report access. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-004 | APP-002 | Oracle Health EHR | APP-020 | Imprivata Enterprise Access Management | Authentication | Consumes | Critical | Clinician access at acquired hospitals may be delayed. | Identity assertions and badge authentication | Medium | Map access profiles to the target EHR. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-005 | APP-002 | Oracle Health EHR | EXT-001 | Enterprise Integration Engine | Data / Interface | Consumes | Critical | Clinical feeds and results may fail during migration. | HL7 and FHIR clinical messages | High | Migrate and reconcile interfaces before retirement. | CMDB / interface catalog / synthetic assessment | Medium | Synthetic organization dependency
DEP-006 | APP-003 | athenaOne | EXT-003 | Enterprise Identity Provider | Authentication | Consumes | High | Ambulatory users may lose SSO access. | SAML and user provisioning | Low | Retain and monitor SSO integration. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-007 | APP-004 | Microsoft Teams Enterprise | EXT-003 | Microsoft Entra ID | Authentication | Consumes | High | Enterprise collaboration access may fail. | Identity, groups, and conditional access | Low | Maintain tenant identity resilience. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-008 | APP-005 | Slack Enterprise Grid | EXT-003 | Microsoft Entra ID | Authentication | Consumes | High | Users may lose access to Slack. | SAML and SCIM provisioning | Low | Remove provisioning after content migration. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-009 | APP-005 | Slack Enterprise Grid | APP-013 | ServiceNow IT Service Management | Workflow | Consumes | Medium | Support alerts and approvals may not reach channels. | Ticket alerts and workflow actions | Medium | Rebuild fourteen required workflows in Teams or ServiceNow. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-010 | APP-006 | Zoom Workplace | EXT-003 | Microsoft Entra ID | Authentication | Consumes | High | Users may lose meeting access. | SAML and user provisioning | Low | Remove provisioning only after disposition. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-011 | APP-006 | Zoom Workplace | EXT-004 | Telehealth Scheduling Gateway | Workflow | Consumes | High | Patient video visits may fail or require manual scheduling. | Appointment links and visit status | High | Validate target capability before committing savings. | CMDB / interface catalog / synthetic assessment | Medium | Synthetic organization dependency
DEP-012 | APP-007 | Microsoft Dragon Copilot | APP-001 | Epic | Data / Workflow | Consumes | High | Ambient notes cannot enter the primary EHR workflow. | Encounter context and draft notes | Medium | Retain certified EHR integration. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-013 | APP-007 | Microsoft Dragon Copilot | APP-002 | Oracle Health EHR | Data / Workflow | Consumes | High | Acquired-hospital clinicians lose integrated documentation. | Encounter context and draft notes | Medium | Retain until EHR consolidation is complete. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-014 | APP-008 | Abridge | APP-001 | Epic | Data / Workflow | Consumes | High | Abridge users cannot capture or return notes in Epic. | Encounter context and draft notes | Medium | Migrate users and templates to Dragon Copilot. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-015 | APP-009 | Nabla Copilot | APP-003 | athenaOne | Data / Workflow | Consumes | Medium | Pilot note workflow stops. | Encounter context and draft notes | High | Export pilot data and terminate connector. | CMDB / interface catalog / synthetic assessment | Medium | Synthetic organization dependency
DEP-016 | APP-010 | Suki Assistant | APP-002 | Oracle Health EHR | Data / Workflow | Consumes | High | Specialty note workflow may be disrupted. | Encounter context and draft notes | Medium | Migrate specialties before consolidation. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-017 | APP-010 | Suki Assistant | APP-003 | athenaOne | Data / Workflow | Consumes | High | Ambulatory note workflow may be disrupted. | Encounter context and draft notes | Medium | Test Dragon coverage for ambulatory specialties. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-018 | APP-011 | QGenda ProviderCloud | APP-017 | Workday Human Capital Management | Data | Consumes | High | Provider demographic and employment data may become stale. | Worker, job, and organization data | Low | Retain governed worker-data feed. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-019 | APP-011 | QGenda ProviderCloud | APP-001 | Epic | Data / Workflow | Provides | High | On-call and provider availability may not be visible to care teams. | Provider schedules and on-call assignments | Low | Monitor schedule integration. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-020 | APP-012 | UKG Pro Workforce Management | APP-017 | Workday Human Capital Management | Data | Consumes | High | Worker and organization data may become inconsistent. | Worker, job, and organization data | Low | Retain governed worker-data feed. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-021 | APP-013 | ServiceNow IT Service Management | EXT-003 | Microsoft Entra ID | Authentication | Consumes | High | IT staff may lose access to incident workflows. | Identity and group memberships | Low | Maintain emergency admin access. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-022 | APP-013 | ServiceNow IT Service Management | EXT-005 | Enterprise Monitoring Platform | Data / Workflow | Consumes | High | Alerts may not generate incidents. | Alerts, events, and service context | Low | Maintain alert integration and reconciliation. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-023 | APP-014 | Jira Service Management | EXT-003 | Microsoft Entra ID | Authentication | Consumes | Medium | Engineering service users may lose access. | Identity and group memberships | Low | Remove after consolidation. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-024 | APP-014 | Jira Service Management | EXT-006 | CI/CD Platform | Workflow | Consumes | Medium | Deployment change evidence may not reach the service desk. | Build, deployment, and change data | Medium | Repoint required workflows to ServiceNow. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-025 | APP-015 | Microsoft Power BI | EXT-007 | Enterprise Data Warehouse | Data | Consumes | High | Executive and operational reporting may become unavailable. | Curated clinical, financial, and workforce data | Low | Maintain governed warehouse connectivity. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-026 | APP-016 | Tableau Cloud | EXT-007 | Enterprise Data Warehouse | Data | Consumes | High | Tableau dashboards may fail during migration. | Curated datasets and extracts | Medium | Rebuild priority dashboards and validate measures. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-027 | APP-017 | Workday Human Capital Management | EXT-003 | Microsoft Entra ID | Authentication | Consumes | High | Employees and HR staff may lose access. | Identity and provisioning | Low | Maintain SSO and emergency access. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-028 | APP-018 | Oracle PeopleSoft HCM | EXT-008 | Legacy Payroll Bank Interface | Data / Interface | Provides | Critical | Payroll files may fail and employees may not be paid correctly. | Payroll payment files and confirmations | High | Complete two parallel payroll cycles before cutover. | CMDB / interface catalog / synthetic assessment | Medium | Synthetic organization dependency
DEP-029 | APP-019 | Salesforce Health Cloud | APP-001 | Epic | Data / Workflow | Consumes | High | Patient and referral context may be incomplete. | Patient, encounter, referral, and care-plan data | Medium | Maintain governed EHR integration and matching. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-030 | APP-019 | Salesforce Health Cloud | APP-002 | Oracle Health EHR | Data / Workflow | Consumes | High | Acquired-hospital patient context may be incomplete. | Patient, encounter, and referral data | Medium | Repoint integration during EHR consolidation. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-031 | APP-020 | Imprivata Enterprise Access Management | EXT-003 | Microsoft Entra ID / Active Directory | Authentication | Consumes | Critical | Enterprise authentication and provisioning may fail. | Users, groups, devices, and policies | Low | Maintain directory resilience and break-glass access. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency
DEP-032 | APP-020 | Imprivata Enterprise Access Management | EXT-009 | Shared Clinical Workstations | Infrastructure | Provides | Critical | Clinicians may lose rapid access to clinical applications. | Endpoint sessions and badge events | Medium | Test endpoint fallback and failover quarterly. | CMDB / interface catalog / synthetic assessment | High | Synthetic organization dependency

## Performance & Roadmap
App ID | Application Name | Availability (12mo) | SLA Target | P1/P2 Incidents (12mo) | MTTR (minutes) | P95 Response Time (seconds) | Business KPI | KPI Actual | KPI Target | Performance Status | Current Release / Version | Lifecycle Stage | Next Minor Release | Next Major Update | Vendor Support End | Contract Renewal Date | Auto-Renew | Exit Notice (days) | Roadmap / Update Notes | Evidence Source | Evidence Confidence
APP-001 | Epic | 99.98% | 99.9% | 12 | 42 | 1.8 | CPOE completion rate | 98.5% | 98% | Meets | May 2026 (synthetic) | Strategic Invest | 2026-09-15 | 2027-03-15 |  | 2027-06-30 | No | 180 | Quarterly optimization and annual major upgrade. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-002 | Oracle Health EHR | 99.85% | 99.9% | 37 | 110 | 2.9 | CPOE completion rate | 91% | 98% | Below | 2026.2 (synthetic) | Consolidation Candidate | 2026-09-30 | 2027-02-01 |  | 2027-01-31 | Yes | 120 | Freeze nonessential customization; prepare phased migration. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-003 | athenaOne | 99.95% | 99.9% | 8 | 55 | 2 | Clean claim acceptance rate | 97.6% | 96% | Meets | Continuous SaaS | Active | 2026-09-20 | 2026-11-15 |  | 2027-03-31 | No | 90 | Continuous vendor releases with quarterly regression testing. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-004 | Microsoft Teams Enterprise | 99.97% | 99.9% | 16 | 35 | 1.4 | Monthly active adoption | 83% | 75% | Meets | Continuous SaaS | Strategic Invest | 2026-09-10 | 2026-10-10 |  | 2027-06-30 | No | 120 | Monthly channel, meeting, security, and AI feature releases. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-005 | Slack Enterprise Grid | 99.93% | 99.9% | 22 | 64 | 1.7 | Monthly active adoption | 49% | 70% | Below | Continuous SaaS | Consolidation Candidate | 2026-09-18 | 2026-10-20 |  | 2026-12-31 | Yes | 90 | Limit changes to security and migration requirements. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-006 | Zoom Workplace | 99.94% | 99.9% | 18 | 71 | 1.9 | Monthly active adoption | 26% | 50% | Below | Continuous SaaS | Review | 2026-09-12 | 2026-09-25 |  | 2026-11-30 | Yes | 60 | Validate telehealth, room, and recording dependencies. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | Low
APP-007 | Microsoft Dragon Copilot | 99.91% | 99.5% | 9 | 48 | 2.2 | Note acceptance without major edits | 88% | 85% | Meets | 2026.07 (synthetic) | Strategic Invest | 2026-09-25 | 2027-01-15 |  | 2027-02-28 | No | 120 | Expand approved specialties after safety and quality review. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-008 | Abridge | 99.78% | 99.5% | 14 | 95 | 2.6 | Note acceptance without major edits | 72% | 85% | Below | Continuous SaaS | Consolidation Candidate | 2026-09-20 | 2026-11-10 |  | 2026-12-15 | Yes | 60 | Pause new enrollment; migrate validated providers. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-009 | Nabla Copilot | 99.6% | 99.5% | 7 | 120 | 3 | Note acceptance without major edits | 38% | 80% | Below | Pilot release | Pilot / Exit Candidate | 2026-09-05 | 2026-12-01 |  | 2026-10-31 | No | 30 | Complete pilot closeout and vendor offboarding. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-010 | Suki Assistant | 99.8% | 99.5% | 11 | 82 | 2.5 | Note acceptance without major edits | 66% | 85% | Below | Continuous SaaS | Consolidation Candidate | 2026-09-22 | 2026-11-20 |  | 2027-01-15 | Yes | 60 | Migrate specialty templates and users in waves. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-011 | QGenda ProviderCloud | 99.92% | 99.9% | 10 | 51 | 1.6 | On-call schedules published on time | 97% | 95% | Meets | 2026 Q2 (synthetic) | Active | 2026-10-01 | 2027-02-20 |  | 2027-04-30 | No | 120 | Quarterly feature adoption and annual integration certification. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-012 | UKG Pro Workforce Management | 99.9% | 99.9% | 15 | 62 | 1.8 | Timecards approved on time | 94% | 95% | Below | Continuous SaaS | Active | 2026-09-28 | 2026-11-12 |  | 2027-05-31 | No | 120 | Correct late-approval workflow before next major release. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-013 | ServiceNow IT Service Management | 99.96% | 99.9% | 19 | 40 | 1.5 | Priority SLA attainment | 92% | 90% | Meets | Current SaaS release | Strategic Invest | 2026-10-05 | 2027-03-01 |  | 2027-07-31 | No | 180 | Expand CMDB quality and AI-assisted service operations. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-014 | Jira Service Management | 99.82% | 99.9% | 28 | 78 | 2.1 | Priority SLA attainment | 74% | 90% | Below | Cloud continuous | Consolidation Candidate | 2026-09-26 | 2026-10-25 |  | 2026-12-31 | Yes | 90 | Migrate service catalogs, queues, assets, and automations. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-015 | Microsoft Power BI | 99.95% | 99.9% | 9 | 43 | 2 | Certified dashboard adoption | 78% | 70% | Meets | Cloud continuous | Strategic Invest | 2026-09-15 | 2026-09-30 |  | 2027-06-30 | No | 120 | Continue semantic model and governed self-service expansion. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-016 | Tableau Cloud | 99.88% | 99.9% | 17 | 91 | 2.8 | Certified dashboard adoption | 32% | 65% | Below | 2026.2 | Consolidation Candidate | 2026-10-05 | 2027-01-20 |  | 2027-02-28 | Yes | 90 | Rebuild high-value dashboards and retire unused extracts. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-017 | Workday Human Capital Management | 99.97% | 99.9% | 13 | 46 | 1.7 | Payroll accuracy | 99.9% | 99.5% | Meets | 2026 R1 (synthetic) | Strategic Invest | 2026-10-10 | 2027-03-15 |  | 2027-08-31 | No | 180 | Prepare regional payroll and benefits expansion. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-018 | Oracle PeopleSoft HCM | 99.7% | 99.9% | 34 | 155 | 3.4 | Payroll accuracy | 99.1% | 99.5% | Below | 9.2 / PeopleTools 8.60 (synthetic) | Replace / Sunset | 2026-09-30 | 2027-09-01 | 2037-12-31 | 2027-12-31 | No | 180 | Freeze customizations and execute phased Workday replacement. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-019 | Salesforce Health Cloud | 99.92% | 99.9% | 12 | 58 | 2.1 | Referral follow-up within SLA | 86% | 85% | Meets | Summer '26 (synthetic) | Active | 2026-09-20 | 2026-10-15 |  | 2027-03-31 | No | 120 | Expand referral automation with governed patient matching. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High
APP-020 | Imprivata Enterprise Access Management | 99.99% | 99.9% | 8 | 29 | 0.9 | Successful badge-tap authentication | 99.7% | 99.5% | Meets | 2026.1 (synthetic) | Strategic Invest | 2026-09-12 | 2027-02-10 |  | 2027-05-31 | No | 180 | Quarterly failover test and endpoint rollout. | Monitoring, service desk, contract calendar, and vendor roadmap; synthetic values | High

## Assumptions
Assumption / Definition | Value | Type / Unit | Notes
Portfolio Name | Northstar Global Health — sample portfolio (fictional) | Text | Fictional healthcare organization used for the hackathon.
As-of Date | 2026-08-14 | Date | Current date for synthetic contracts, releases, and evidence.
Usage Lookback (days) | 90 | Days | Active users are based on a synthetic 90-day lookback.
CIO Savings Target | 15% | Percent | Required reduction target from the hackathon prompt.
Safe Savings Confidence | High | Allowed value | Only high-confidence actions are counted as safe savings.
Avoidable Annual Savings | Recurring annual run-rate spend that disappears after an action is completed. | Definition | Excludes continuing commitments and one-time transition costs.
First-Year Net Savings | Avoidable annual savings less one-time transition cost, floored at zero. | Definition | Transition costs are modeled separately from recurring savings.
Public Product Facts | Real application names, vendors, and high-level capabilities come from official vendor pages. | Data treatment | See Sources sheet.
Organization-Specific Data | All costs, users, contacts, scores, risks, performance, dependencies, deployment details, and dates are synthetic. | Data treatment | Do not present as facts about any real healthcare organization.
Stakeholder Interviews | Not performed in this iteration. | Constraint | Use automated evidence and confidence flags; missing evidence should produce Needs Validation.
Patient Data | No patient-level or protected health information is included. | Safety | Dataset is for application rationalization prototyping only.

## Data Dictionary
Required Data Area | Workbook Sheet(s) | Fields | Definition | Data Classification | No-Interview Proxy Source | MVP Use
Application Name and Description | App Inventory | App ID; Application Name; Short Name; Description | Organization terminology, unique identifier, and high-level purpose/capabilities. | Public product name + synthetic organization record | CMDB or application inventory; vendor product pages | Yes
Technical Specs | App Inventory | Commercial Model; Hosting Model; Platform; Development / Configuration Language | Deployment, platform, commercial model, and extension/configuration technology. | Public high-level product facts + synthetic deployment | CMDB; architecture repository; automated discovery; vendor documentation | Yes
Number of Users | User Profiles; App Inventory | Access Level; Entitled Users; Active Users 90d; Inactive Users 90d; Utilization Rate | Access-level user counts and recent usage without listing real individuals. | Synthetic | IAM/SSO logs; license admin export; application telemetry | Yes
Vendor Information | App Inventory; Sources | Vendor; Product URL; Support URL; Vendor Account Contact | Vendor identity and public product/support channels; account contacts are placeholders. | Public vendor + synthetic contact | Contract repository; procurement system; vendor website | Yes
Application Owner | App Inventory | Application Owner; Owner Role; Owner Email | Person accountable for key application decisions. | Synthetic placeholder | CMDB ownership fields; governance records | Yes
Technical SMEs | App Inventory | Technical SME; SME Role; SME Email | Technical subject matter expert for platform, operations, or architecture. | Synthetic placeholder | Support roster; architecture repository; on-call directory | Yes
Defined Capabilities | Capability Map | Capability ID; Capability; Process / Tasks; Support Role; Coverage Level; Capability Criticality | Many-to-many application-to-capability mapping used to identify meaningful redundancy. | Synthetic organization mapping | Process taxonomy; architecture repository; application documentation; AI-assisted normalization | Yes
Risk Indicators | Risks | Category; Description; Severity Score; Likelihood Score; Risk Score; Risk Level; Mitigation; Status | Security, regulatory, continuity, technical, AI, and vendor risks with mitigations. | Synthetic | Security scans; GRC; BCP/DR records; service desk; vendor assessments | Yes
TCO | TCO | License; Maintenance; Infrastructure; Vendor Services; Internal Labor; Education; Annual TCO; Avoidable Annual Cost | Annual run-rate cost components plus the portion removable after an action is complete. | Synthetic | Contracts; AP spend; cloud billing; time allocation; training budget | Yes
Business Value | App Inventory; Capability Map | Business Criticality; Business Value Score; Rationale; Critical Operation Flag | Illustrative value and criticality based on capability, use, and operational role. | Synthetic proxy assessment | Capability criticality; usage; process criticality; regulatory obligations | Yes
Performance Tracking | Performance & Roadmap | Availability; SLA; Incidents; MTTR; Response Time; Business KPI; Status | Technical and business performance measures derived without stakeholder interviews. | Synthetic | Monitoring; service desk; application telemetry; operational reports | Yes
Dependencies | Dependencies | Source; Target; Type; Criticality; Impact; Data Exchanged; Migration Feasibility | Application, platform, data, authentication, workflow, and infrastructure dependencies. | Synthetic | CMDB; integration catalog; network and API discovery; architecture records | Yes
Scheduled Updates and Upgrades | Performance & Roadmap | Current Release; Next Minor Release; Next Major Update; Vendor Support End; Update Notes | Release calendar, planned upgrades, and support horizon. | Synthetic deployment dates + public vendor context | Vendor roadmap; release calendar; change-management records | Supporting
Lifecycle Stages | Performance & Roadmap; App Inventory | Lifecycle Stage; Contract Renewal; Exit Notice Days | Current lifecycle posture and key timing constraints. | Synthetic | Application lifecycle register; contracts; product roadmap | Yes
No-Interview Evidence Controls | App Inventory; all detail sheets | Evidence Source; Evidence Confidence; Data Status | Makes clear which values are evidence-based, inferred, missing, or synthetic. | Synthetic dataset control | Automated system evidence only; no stakeholder attestation | Yes
Expected Test Outcomes | QA Expected Output | Expected Disposition; Target; Rationale; Preconditions; Safe Savings | Ground truth for testing the prototype; never provide this sheet to the recommendation engine. | Synthetic QA control | Scenario design | QA only

## Sources
App ID | Application Name | Vendor | Official Product URL | Public Facts Used | Verified Date | Source Type | Synthetic Data Note
APP-001 | Epic | Epic Systems Corporation | https://www.epic.com/about/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-002 | Oracle Health EHR | Oracle Corporation | https://www.oracle.com/health/clinical-suite/electronic-health-record/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-003 | athenaOne | athenahealth, Inc. | https://www.athenahealth.com/solutions/athenaone | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-004 | Microsoft Teams Enterprise | Microsoft Corporation | https://www.microsoft.com/en-us/microsoft-teams/enterprise | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-005 | Slack Enterprise Grid | Salesforce, Inc. | https://slack.com/enterprise | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-006 | Zoom Workplace | Zoom Communications, Inc. | https://www.zoom.com/en/products/collaboration-tools/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-007 | Microsoft Dragon Copilot | Microsoft Corporation | https://www.microsoft.com/en-us/health-solutions/clinical-workflow/dragon-copilot | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-008 | Abridge | Abridge AI, Inc. | https://www.abridge.com/product | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-009 | Nabla Copilot | Nabla | https://www.nabla.com/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-010 | Suki Assistant | Suki AI, Inc. | https://www.suki.ai/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-011 | QGenda ProviderCloud | QGenda, LLC | https://www.qgenda.com/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-012 | UKG Pro Workforce Management | UKG, Inc. | https://www.ukg.com/products/ukg-pro-workforce-management | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-013 | ServiceNow IT Service Management | ServiceNow, Inc. | https://www.servicenow.com/products/itsm.html | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-014 | Jira Service Management | Atlassian | https://www.atlassian.com/software/jira/service-management | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-015 | Microsoft Power BI | Microsoft Corporation | https://www.microsoft.com/en-us/power-platform/products/power-bi | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-016 | Tableau Cloud | Salesforce, Inc. | https://www.tableau.com/products/tableau | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-017 | Workday Human Capital Management | Workday, Inc. | https://www.workday.com/en-us/products/human-capital-management/overview.html | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-018 | Oracle PeopleSoft HCM | Oracle Corporation | https://www.oracle.com/applications/peoplesoft/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-019 | Salesforce Health Cloud | Salesforce, Inc. | https://www.salesforce.com/healthcare/cloud/ | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.
APP-020 | Imprivata Enterprise Access Management | Imprivata, Inc. | https://www.imprivata.com/products/access-management/enterprise-access-management | Product name, vendor, high-level delivery model, and public capability description. | 2026-08-14 | Official vendor product page | All organization-specific costs, users, owners, SMEs, scores, risks, performance, dependencies, deployment details, and dates are synthetic.